## Sheet1
Week 1 :
Serial Number | Task Name | Task Description | Status
1 | Task to create Protimer application project and select pin configurations
2 | Task to add FreeRTOS Feature to Protimer_Application Projection | Try with manual way
3 | Task to create multiple threads and do a context switch between threads | Configure Preemptive / Co-operative scheduling
4 | Task to add a Watchdog timer feature and refresh wherever it requires. | Configure IWDG to reset the mcu within 5 sec if it not feeding and try for various time configs
5 | Task to read GPIO using external interrupt method | GPIO interrupt method should support for Switch Debouncing feature.
6 | Task to Control LED's and its API implementation using bitwise operations. | API should receive uint8_t argument and control specific LED and it should be reusable
7 | Port existing protimer project to STM32 | Observe the functionality
Week 2 :
Serial Number | Task Name | Task Description | Status
1 | Add RTC feature and its API creation | Read HH:MM:SS input from user and configure it to RTC
2 | Handling of Exception errors in RTC | Minimum and mximum configurable time
3 | Understanding the concept of +UTC Time and its conversion to RTC | Add a driver support of SNTP and test it manual way.
4 | Create FreeRTOS Timers to expire at scheduled time intervals | LED state should change at every firing
5 | Add CLI Scripting feature to know the Device health status | Print the Health status and various parameters
Week 3 :
Serial Number | Task Name | Task Description | Status
1 | Task to write Basic API's for SD Card communication | Should me portable, reusable and modular
2 | Task to write Erase sector, chunk and fullchip | change the configurations and try
3 | Task to write 1 Byte of data into SD Card and its validation using memcpy | Use memory browser tools to validate
4 | Task to write 1 KB of data into SD Card and its validation using memcpy | Use memory browser tools to validate
5 | Task to write Full chip of data into SD Card and its validation using memcpy | Use memory browser tools to validate
Week 4 :
Serial Number | Task Name | Task Description
1 | Task to write Basic API's for File creation, rename and delete using fs ?
2 | Task to create file using current date as file name and write data into it ?
3 | Task to create file using current date as file name with a maximum size ?
4 | Task to create files using multiple dates ?
5 | Task to monitor the SD Card space availability and remaining space ?
6 | Monitor the SD Card space availability, If it exeeds delete largest file ?
7 | Task to list and sort the files based on name ?
Target Date 45 days from 27-07-2025
OLED Display communication using I2C
BUZZER
SPEAKER